## Slide 1: (CDR-2417) Optimizing The Resolution of Disputes
Lynn B. Larsen, CFCC
Lynn@LarsenAnalytics.com
801-541-9155

## Slide 3: Please use microphone for all questions and comments!

## Slide 4: Dispute Resolution: The Default Option
Court Litigation:
  Decision by Judge or lay jury
  Requires an Attorney
  Public
  Right to Appeal to higher court
  Typically takes years
  Can become very costly

## Slide 5: Actual Case (Typical)
Contract signed in December 2009: $500,000
Construction December 2009 to January 2011.
March 2011, Contractor filed suit
(alleging delays and extra work)
Owner counterclaimed for Defective Work.
April 2016 Trial before jury.
March 2017 Judgment against Contractor.

## Slide 6: Case Docket:

## Slide 7: Court Litigation vs ADR
The Cost and Delayed Resolution of Court Litigation led the Construction Industry to investigate Alternative Dispute Resolution (ADR) Methods

## Slide 8: Alternative Dispute Resolution (ADR)
Negotiation
Mediation
Arbitration
Dispute Resolution Board (DRB)

## Slide 9: Alternative Dispute Resolution (ADR) Methods
Negotiations
  Early Resolution
  In direct control
  No attorney necessary
  Timely
  Little Cost
  Does not work unless both parties want to resolve

## Slide 10: Alternative Dispute Resolution (ADR) Methods
Mediation
  Negotiation facilitated by neutral third party
  Not Binding
  Parties in control of dispute resolution
  Gain understanding of other party’s position
  If one party has no interest in resolving dispute, then mediation is a waste

## Slide 11: Alternative Dispute Resolution (ADR) Methods
Mediation
  Pure Mediation
  Evaluative Mediation
  Binding Mediation

## Slide 12
Arbitration before 1 or 3 arbitrators
  Private
  Skilled Decision Maker
  Generally Less Costly than Litigation
  Resolution generally quicker than Litigation
  Less Formal than Litigation
  But can still become lengthy and expensive if Discovery is allowed.

## Slide 13: Arbitration vs Litigation

## Slide 14: Arbitration vs Litigation

## Slide 15: Arbitration vs Litigation

## Slide 16: Alternative Dispute Resolution (ADR) Methods
Arbitration Providers:
1. American Arbitration Association (AAA)
www.adr.org
2. Construction Dispute Resolution Services (CDRS)
www.constructiondisputes-cdrs.com
3. JAMS
www.jamsadr.com
4. Other Private organizations

## Slide 17: DRB = Dispute Resolution Board
At time of contracting, parties jointly select 3 individuals to be “jobsite judges.”
  Unbiased, Knowledgeable, Available
The jobsite judges are to DRB
If a dispute arises, either party can call on the DRB to resolve the dispute
DRB issues non-binding “Recommendation”
Parties use the Recommendation to resolve the dispute

## Slide 18: Dispute Resolution Board (DRB)
Decision by pre-selected knowledgeable persons
Decision is a Non-binding Recommendation
Dispute Resolved in “Real Time”
No need for Discovery –Everyone still available
Private

## Slide 20: Dispute Review/Resolution Board (DRB)
Can be selected soon after contract award OR After a Dispute arises
    Most effective, If selected before construction begins:
      DRB members become familiar with project,
      keep current with ongoing progress of the work and
      Meet periodically with parties (monthly, quarterly, or ?)
      Ready to address problems and disputes
      Many disputes are avoided
      Holds DRB Hearings as needed
    If after dispute arises, then DRB holds hearings to address disputes:
      Can then select DRB members with expertise in field of dispute

## Slide 21: Dispute Resolution Board Foundation
  -- “a non-profit organization dedicated to promoting the avoidance and resolution of disputes worldwide using the unique and proven Dispute Resolution Board (DRB) method.”
  www.DRB.org

## Slide 22: DRBF:

## Slide 23: Alternative Dispute Resolution (ADR) Methods
  -- Negotiations
  -- Mediation
  -- Arbitration
  -- Dispute Review/Resolution Board (DRB)

## Slide 24: Typical disputes that arise on a construction project

## Slide 25: Issue: Failure to Cooperate
Under covenant of good faith and fair dealings, each party impliedly promises that he will not intentionally or purposely do anything which will destroy or injure other party's right to receive fruits of the contract.

## Slide 26: Issue: Failure to Cooperate
Who can best correctly and timely determine merits of a dispute alleging “Failure to Cooperate?”
  A judge or jury
  An Arbitrator
  A DRB panel
Who would you want?

## Slide 27: Issue: Differing Site Condition
Project: Replace earthen dam after reservoir drained
First remove ~ 400,000 cubic yards of material
Then place ~ 400,000 cubic yards of material
Specification:
- keep ground water 3’ below level of excavation.

## Slide 28: Issue: Differing Site Condition
No problem for first 380,000 cubic yards of removal
-Then not able to maintain water level as specified
- Engineer issued repeated Stop Notices
- Contractor attempts multiple dewatering methods w/o success
-Contractor claims DSC; Denied by Owner
- Minimal progress June thru August

## Slide 29: Typical Issues: Differing Site Conditions

## Slide 30: Issue: Differing Site Conditions
-From June thru Aug, Contractor attempts to perform
with minimal progress
- Owner issues Repeated Stop Notices
After 3 months, on a weekend without Owner on site Contractor VP visits site and drives sheetpiles to control water and finishes excavation

## Slide 31
Actual Result (Mediation after suit filed)
  Contractor justified claim for $2 million overrun
  Contractor dismissed Project Manager
  Project finished 1 year late
  Owner Acknowledged fault but could only gather $1 million. Alternative was for contractor to own water system, reservoir, and dam
  Owner Lost and paid $1 million
  Contractor Won but lost $1 million

## Slide 32
Who can best correctly and timely determine merits of a dispute alleging “Differing Site Conditions Claim?”
  A judge or jury
  An Arbitrator
  A DRB panel

## Slide 33: Issue: Differing Site Condition
How would result have been different if DRB panel had existed?
    Prompt review in June before $1M spent
    Both parties would have saved legal expenses
    Owner would not have lost $1 million
    Contractor would not have lost $1 million
    Timely completion of Project
    Project Manager might still have job

## Slide 34: Typical Issues: Defective Plans
Defective Plans:
  Plan Omissions or Conflicts
  Who has duty to coordinate plans?
    Failure to have coordinated plans
    Mechanical and structural plans

## Slide 35: Issue: Failure to Coordinate Plans

## Slide 36: Plans Not Coordinated
Contractor gave Notice: Plans not coordinated
Owner Alleges: Contractor’s Duty to coordinate
Contractor redesigns systems: Extra cost and time
Contractor submits claim
Arbitration starts 1 year later, lasts 6 months

## Slide 37: Arbitrators’ Ruling:
Contractor had duty to give Notice
Then architect had duty to resolve conflicts
Contractor recovered all extra expense
Real Result: Contractor went out of business

## Slide 38: Defective Plans Claim
How would result have been different if DRB panel had existed?
--DRB: timely advise that Architect had duty to coordinate
--Architect: would have redesigned
--Contractor: would have been paid for any extra work
--Contractor would still be in business

## Slide 39: Issue: Loss of Productivity
Who is Responsible for losses in Productivity
AACE's RP No. 25R-03:
Estimating Lost Labor Productivity In Construction Claims:
---identifies 25 causes of labor productivity losses

## Slide 40: Issue: Loss of Productivity
  1. Absenteeism and the missing man syndrome
2. Acceleration (directed or constructive)
3. Adverse or unusually severe weather
4. Availability of skilled labor
5. Changes, ripple impact, cumulative impact of multiple changes and rework
6. Competition for Craft Labor
7. Craft turnover
8. Crowding of labor or stacking of trades

## Slide 41: Issue: Loss of Productivity
9. Defective engineering, engineering recycle and/or rework
10. Dilution of supervision
11. Excessive overtime
12. Failure to coordinate trade contractors, subcontractors and/or vendors
13. Fatigue
14. Labor relations and labor management factors
15. Learning Curve
16. Material, tools and equipment shortages
17. Over-manning

## Slide 42: Issue: Loss of Productivity
18. Poor morale of craft labor
19. Project management factors
20. Out of sequence work
21. Rework and errors
22. Schedule Compression Impacts on Productivity
23. Site or work area access restrictions
24. Site conditions
25. Untimely approvals or responses

## Slide 43: Issue: Loss of Productivity
Who can best correctly and timely determine merits of a dispute alleging “Disruption causing a loss in Productivity?”
  A judge or jury
  An Arbitrator
  A DRB panel
Who would you want?

## Slide 44: Issue: Delay or Disruption
Who can best correctly and timely determine merits of a delay dispute?
  A judge or jury
  An Arbitrator
  A DRB panel
Who would you want?

## Slide 45: Issue: Delay or Disruption
Evaluation includes
  Determination of causes of delay
  Determine party responsible
  Determine Impact: Analyses of CPM schedule and Cost

## Slide 46: Issue: Scope Change
Scope Change or Mere Clarification
  Who can best determine merits of allegation

## Slide 47: Damages: an Issue in All Disputes
Legal Standard:
Put party back into position it would have been if the default by the other party had not occurred.
Who can best determine?
  A judge or jury
  An Arbitrator
  A DRB panel
Who would you want?

## Slide 48: What process do you want to Resolve disputes?

## Slide 49: Issue: ADR Recommended Practice
Litigation with judge or jury?
Mediation (assisted negotiation)
Arbitration?
Dispute Resolution Board?

## Slide 50: ADR: MY Recommended Practice
Dispute Resolution Board (DRB)
  Private
  In “Real Time”
  By knowledgeable persons
  Less costly
  More timely
  But remember, DRB only gives Recommendations
    Then parties must resolve

## Slide 51: Dispute Resolution Board (DRB)
Decision by pre-selected knowledgeable persons
Decision is a Non-binding Recommendation
Dispute Resolved in “Real Time”
No need for Discovery –Everyone still available
Private

## Slide 53: Avoidance and Prevention

## Slide 54: Avoidance and Prevention
Shared Communications
Partnering
Bid Document Escrowing
Clear Contract Language
Assumption of Risk
Document Exchange
Presence of DRB prompts parties to resolve disputes

## Slide 55: Avoidance and Prevention
Disputes are avoided or lessened if the contract documents address anticipated risks in clear unambiguous terms.

## Slide 56: Clear Unambiguous Contract Terms
1. Notice provisions.
2. Reliance on pre-contract representations.
3. Claim waivers and releases required with pay applications.
4. Fire, weather, natural calamity, and other force majeure issues
5. Delay and disruption costs.
6. Changes.
7. Dispute resolution processes.
8. Insurance obligations.
9. Indemnity provisions.
10. Assessment of consequential damages
11. Guarantees of performance.
12. Coordination of work or equipment furnished by others.

## Slide 57: Clear Unambiguous Contract Terms
13. Termination for convenience limitations and conversions.
14. Venue and choice of law provisions.
15. Coordinate of contract drawings.
16. Designation of design responsibility: design or performance specifications
17. Liquidated damages
18. Attorney fees
19. Differing Site Conditions
20. Code compliance
21. Site Access
22. Labor availability

## Slide 59: Questions/comments? (Please use microphone)